## Sheet1
|  | Farid Shabri | Amirul Hakimi | Iqbal Fauzi | Amjad Malik | Amit Chakma | Abdul-Azeez Olanlokun
Week | Task to do | 1) Set-up Github repository | 1) Model requirement diagram | 1) Discussion on main idea project | 1) Discussion on main idea project | 1)Discussion on main idea project | 1) Discussion on main idea project | Notes | Summary/Feedback
1 |  | 2) Model requirement diagram | 2) Setting up and edit documents |  | 2) Provides overview Use Case |  | 2)First sketch of idea |  | edit Use Case
12/04-18/04 |  | 3) Use Case Diagram | [6 empty] | specify entities and relation
specify stakeholder- humans that be rescued, operation
constrain diagram- reduce all contexts, like scenario carrying person, putsize of human
refine use case- sequence and activity diagram
| Attendance | Attended | Attended | Attended | Attended | Attended | Attended
Week | Task to do | 1) Correct the Use Case Diagram | 1) Block Diagram | 1)Discussion on scenarios | 1) Discussion on Scenarios | 1)Discussion on Scenarios | 1) Discussion on Scenarios | Notes | Summary/Feedback
2 |  | 2) Block Diagram | 2) Discussion on Scenarios | 2)Creating Activity Diagram | 2) Creating Sequence Diagram | 2)Creating State Machine Diagram | 2) Responsible for Contraint Diagram |  | Edit Github repository
19/04 -25/04 | [8 empty] | Block Diagram (subsystem instead of bdd)
Activity diagram ( fork and joint)
Insert prototype
Adding on land scenario
| Attendance | Attended | Attended | Attended | Attended | Attended | Attended
Week | Task to do | 1) Restructure Github repository |  | 1) Creating Activity Diagram on Land | 1) Modify Sequence Diagram (water scenario) |  |  | Notes | Summary/Feedback
3 |  | 2) First Sketch drawing |  | 2)Discussion of Robot's Prototype | 2) Creating Sequence Diagram (Land Scenario)
26/04 -02/05
| Attendance | Attended | Attended | Attended | Attended | Attended | Attended